## Daily Activity Log
Date | Day | Activity | Status | Hours
01-Jun-2026 | Monday | Project planning, requirement analysis, selected Smart Agriculture Monitoring System as final project | Completed | 3
02-Jun-2026 | Tuesday | Studied AI applications in agriculture and disease detection | Completed | 3
03-Jun-2026 | Wednesday | Researched CNN, MobileNetV2 and transfer learning | Completed | 3
04-Jun-2026 | Thursday | Explored PlantVillage dataset and disease categories | Completed | 3
05-Jun-2026 | Friday | Downloaded dataset and organized folders | Completed | 3
06-Jun-2026 | Saturday | Reviewed preprocessing techniques | Completed | 3
07-Jun-2026 | Sunday | Weekly documentation and research notes | Completed | 2
08-Jun-2026 | Monday | Designed overall project workflow | Completed | 3
09-Jun-2026 | Tuesday | Studied TensorFlow and Keras APIs | Completed | 3
10-Jun-2026 | Wednesday | Configured Python environment and required libraries | Completed | 3
11-Jun-2026 | Thursday | Dataset cleaning and verification | Completed | 3
12-Jun-2026 | Friday | Image augmentation experiments | Completed | 3
13-Jun-2026 | Saturday | Prepared preprocessing pipeline | Completed | 3
14-Jun-2026 | Sunday | Weekly review and documentation | Completed | 2
15-Jun-2026 | Monday | Built first CNN training pipeline | Completed | 4
16-Jun-2026 | Tuesday | Tested MobileNetV2 architecture | Completed | 4
17-Jun-2026 | Wednesday | Hyperparameter tuning | Completed | 3
18-Jun-2026 | Thursday | Model evaluation and validation | Completed | 3
19-Jun-2026 | Friday | Improved dataset organization | Completed | 3
20-Jun-2026 | Saturday | Recorded model observations | Completed | 3
21-Jun-2026 | Sunday | Weekly documentation | Completed | 2
22-Jun-2026 | Monday | Designed backend architecture using FastAPI | Completed | 3
23-Jun-2026 | Tuesday | Developed prediction API | Completed | 4
24-Jun-2026 | Wednesday | Implemented image upload functionality | Completed | 3
25-Jun-2026 | Thursday | Added disease prediction endpoint | Completed | 3
26-Jun-2026 | Friday | Integrated treatment recommendation module | Completed | 3
27-Jun-2026 | Saturday | API testing | Completed | 3
28-Jun-2026 | Sunday | Weekly review | Completed | 2
29-Jun-2026 | Monday | Planned website UI and navigation | Completed | 3
30-Jun-2026 | Tuesday | Created landing page wireframe | Completed | 3
01-Jul-2026 | Wednesday | Developed frontend components using React | Completed | 4
02-Jul-2026 | Thursday | Implemented login and registration pages | Completed | 3
03-Jul-2026 | Friday | Added responsive dashboard layout | Completed | 3
04-Jul-2026 | Saturday | Developed image upload interface | Completed | 4
05-Jul-2026 | Sunday | Weekly documentation | Completed | 2
06-Jul-2026 | Monday | Connected frontend with backend APIs | Completed | 3
07-Jul-2026 | Tuesday | Tested API integration | Completed | 4
08-Jul-2026 | Wednesday | Improved prediction result interface | Completed | 3
09-Jul-2026 | Thursday | Added confidence score display | Completed | 3
10-Jul-2026 | Friday | Implemented disease treatment suggestions | Completed | 3
11-Jul-2026 | Saturday | UI refinement | Completed | 3
12-Jul-2026 | Sunday | Weekly review | Completed | 2
13-Jul-2026 | Monday | Trained model using complete dataset | Completed | 4
14-Jul-2026 | Tuesday | Evaluated validation accuracy | Completed | 3
15-Jul-2026 | Wednesday | Fine tuned MobileNetV2 | Completed | 3
16-Jul-2026 | Thursday | Saved trained model and generated reports | Completed | 3
17-Jul-2026 | Friday | Performed prediction testing | Completed | 3
18-Jul-2026 | Saturday | Fixed preprocessing issues | Completed | 4
19-Jul-2026 | Sunday | Weekly documentation | Completed | 2
20-Jul-2026 | Monday | Tested prediction accuracy on multiple crops | Completed | 4
21-Jul-2026 | Tuesday | Debugged incorrect disease predictions | Completed | 4
22-Jul-2026 | Wednesday | Improved model loading process | Completed | 3
23-Jul-2026 | Thursday | Updated prediction pipeline | Completed | 3
24-Jul-2026 | Friday | Backend optimization | Completed | 3
25-Jul-2026 | Saturday | Deployment preparation | Completed | 3
26-Jul-2026 | Sunday | Weekly review | Completed | 2
27-Jul-2026 | Monday | Deployed backend and frontend | Completed | 8
28-Jul-2026 | Tuesday | Fixed deployment issues and environment configuration | Completed | 6
29-Jul-2026 | Wednesday | Tested hosted website, corrected prediction errors and improved usability | Completed | 5
30-Jul-2026 | Thursday | Final debugging, documentation, README, GitHub updates and successful project completion | Completed | 5